## Instructions
Guidance to Veeco for upgrading RedBull from CCF 3.4 to CCF 3.6.1
Instructions
| General | This is an analysis of the work required to upgrade RedBull from CCF 3.4 to 3.6.1. We have divided the analysis into three sections as summarized below. Refer to each Tab for specific details.
The impact to Veeco RedBull had been estimated as: None, Minor, Moderate, Major, Optional. None is indicated by the character '-'.
Tab 1: CCF 3.6.1 Recompile
Recompile CCF 3.6.1 using Visual Studio 2010, changing the target framework to .NET 4 for all projects
Tab 2: Porting to CCF 3.6.1
Reapply certain changes, made to CCF 3.4, to CCF 3.6.1
Tab 3: Release Notes 3.5-3.6.1
Change RedBull to keep up with features/fixes/changes in CCF releases since CCF 3.4

## 1. CCF 3.6.1 Recompile
To use CCF 3.6.1 with RedBull, CCF must be compiled to the .NET 4.0 framework using Visual Studio 2010. The CCF Continuous Integration solution can then be used to execute the product's unit tests to validate the code. This Tab contains our notes from these processes to advise you what to expect. The first section covers recompiling. 1. Open CCF CI.sln using VisualStudio 2010. 2. For each Project, set the Target Framework to .NET 4.0 3. Resolve Reference errors (see data below) 4. Build the solution to ensure no compiler errors. 5. Resolve compiler warnings (optional). The Affected Project and Reference Target columns help identify References to resolve. The Action Required column describes actions required by Veeco, and the Effort column provides a rough estimate. The second section covers executing CCF Unit Tests. Some actions are required to ensure that tests will pass.
Recompile CCF 3.6.1 with VS2010 and .NET 4.0
Issue | Affected Project | Reference target | Action Required | Effort
Reference error | EquipmentUnitTests UsersUnitTests Equipment GuiCommon IO OIClient OIServer Recipes Simulation | System.Runtime.Serialization, System.ServiceModel | Resolve reference be removing and re-adding reference | Minor
Reference error | OIServer | System.Workflow.ComponentModel | Resolve reference be removing and re-adding reference | Minor
Reference error | IOUnitTests | OpcNetApi, OpcNetApi.Com | Resolve reference be removing and re-adding reference | Minor
Reference error | InstallationAssistantUnitTests | RhinoMocks.dll Interop.IWshRuntimeLibrary | Resolve reference be removing and re-adding reference | Minor
Reference error | GuiScreens | PresentationCore PresentationFramework WindowsBase WindowsFormIntegration Interop.CMSLib System.Windows.Forms.DataVisualilzation | Resolve reference be removing and re-adding reference | Minor
Reference error | CxCOMReferences | Many references change from Xxxx to Interop.Xxxx including MSXML2. | Resolve reference be removing and re-adding reference. Also set all references to Embed Interop Types = False and Copy Local = False | Minor
Reference error | GuiCommonUnitTests | Remove GuiCommon, readd Cimetrix.GuiCommon | Resolve reference be removing and re-adding reference | Minor
Reference must be added | RVC162Visualization GuiScreens BrooksM2QuadVisualization BrooksM2QuadScreens | System.Xaml | Add reference | Minor
Compiler warning | Equipment\EquipmentLoader.cs |  | Add (System.Type) cast to EquipmentInterfaceFilter(), Line 213 | Optional override
Execute CCF CI.sln Unit Tests
UnitTests needing MySQL database fail, because VS2010 needs update to MySQL Connector Net |  |  | Download latest MySQL Connector Net 6.5.x Uninstall MySQL Connector Net 5.1.7, install 6.5.x. Copy MySql.Data.dll to Source\Shared. | Minor
Reference error | InstallationAssistant InstallationAssistantUnitTests OIServerUnitTests FactoryAutomationUnitTests | MySql.Data reference | Resolve reference be removing and re-adding reference | Minor
When executing CI build unit tests, many errors in HistoryUnitTests project: "Unknown database ccf_test_db" | HistoryUnitTests |  | Need patch to HistoryUnitTests\MySqlEptHistoryTest.cs to create a ccf_test_db database. Contact Cimetrix. [10/2/12] | Minor

## 2. Porting to CCF 3.6.1
This Tab lists each file from CCF 3.4 which had been previously modified to support RedBull, generally known as "overrides". In order to retain functionality for RedBull, some of the overrides need to be reapplied to the new version of CCF. The data organization is as follows: The CCF package and file are named. The Purpose column recounts the origin of the change. The Impact column describes actions required by Veeco, and the Effort column provides a rough estimate. "Reapply" indicates the same change should be applied to the same file in CCF 3.6.1. "Do not maintain override" means no change is expected to the file. The information is presented in alphabetical order by package; an actual order for performing the work is not prescribed. The second section identifies classes in RedBull which are copies of CCF classes. Improvements made to the original CCF classes may be desireable in the Veeco product.
Delta, Veeco 3.4 to CCF 3.4
Package | Class | Purpose | Porting Impact to Veeco | Effort?
All projects | AssemblyInfo.cs | Version reference to the CCF release and build | Ignore difference | -
Several projects | *.Designer.cs | Different runtime version | Ignore difference. Due to VS2010/.NET4 recompile | -
Alarms\Alarms | AlarmClientService.cs | Do not want exception from RegisterAlarms if the alarm is already registered, want only to log. | Reapply | Minor
CimStoreData\CimStoreData | DataServer.cs | Data sets prepend "Cimetrix." related to creating separate schemas for their database to better differentiate between default Cimetrix data and Veeco data | Reapply | Minor
Common\Common\Commands | ActiveObject.cs | Wanted ActiveObject.Run() to be overrideable, wanted to be able to stop it, wanted to be able to check if AO is alive. | Do not maintain override. Customer change - RedBullComponent should use their SimpleActiveObject as invoker if desired, implement IsActiveObjectAlive. Note they may need calls to Start components, see RedBull*EquipmentControlSystem.CreateEquipmentComponents. | Moderate
Common\Common\Commands | Command.cs ICommand.cs | Wanted a command completion callback. | Reapply | Minor
Configuration\Configuration | ConfigurationClientService.cs IConfigurationClientService.cs | Added GetParameterTree | Not incorporated; reapply. Veeco's *ConfigurationClientCommunicator classes rely on the GetParameterTree API to be available. | Minor
Configuration\Configuration | ConfigurationContract.cs | Wanted GetParameterTree, GetChildBranchNames added | Partially incorporated; Do not maintain override. Cimetrix changes: IConfiguration added GetChildBranchNames; IConfigurationOI added GetChildBranchNames and GetParameterTree. Veeco implements RedBullCommons.IConfigurationClient which makes up for Cimetrix IConfiguration NOT including the GetParameterTree API. | -
Equipment\Equipment\Components | Component.cs | Wanted statusVariables array declared protected not private | Incorporated; Customer to change use from private field statusVariables to protected property StatusVariables | Minor
Equipment\Equipment\Components | LoadPort.cs | Null check | Fixed; Do not maintain override | -
Equipment\EquipmentUnitTests | LoadPortTest.cs | Sleep | Fixed; Do not maintain override | -
FactoryAutomation\FactoryAutomation | MidasEventProvider.cs | Code removed 1/13/2011 TH, root cause presumed fixed in 3.5 | Presumed fixed; Do not maintain override | -
FactoryAutomation\FactoryAutomation | CimConnectServices.cs + RemoteCommandHandler.cs | Add ability to customize a Remote Command Handler callback. During Dispose, does not unregister as remote command handler. | Incorporated; Do not maintain override | -
FactoryAutomation\FactoryAutomation | COMHelper.cs |  | Incorporated; Do not maintain override | -
FactoryAutomation\FactoryAutomation | MsgId.cs | Added constants | Incorporated; Do not maintain override | -
FactoryAutomation\FactoryAutomationClient | FactoryAutomationClientService.cs | GEM event posting should include all Variables not just DataVariables | Fixed; Do not maintain override | -
FactoryAutomation\FactoryAutomationClient | Variable.cs | Added events to Variable.cs so interested parties can be notified when a status variable is set or actually changed | Not incorporated Reapply likely. Customer choice: similar functionality available from DataClientService CreateChangeRequest. | Moderate
FactoryAutomation\FactoryAutomationClient | RemoteCommand.cs | Added RemoteCommand and RemoteCommandParameter | Incorporated; Do not maintain override | -
FactoryAutomation\FactoryAutomationClient | FactoryAutomationClientService.cs IFactoryAutomationClientService.cs IFactoryAutomationServer.cs | Added RegisterRemoteCommand API | Incorporated; Do not maintain override | -
FactoryAutomation\FactoryAutomationUnitTests | MockCIMConnect.cs | ICxClientApplication Register/UnregisterECChanged APIs implemented (this looks like a correction to CCF) | Ignore difference Code has been superceded by other tests, change no longer applies | -
GUI\GuiCommon | BaseScreen.cs | Modified BaseScreen Class to restrict the polling from BaseScreen to OIInterfaces classes. This change will let the Basescreen to propagate the data to OIInterface only if any change happens in the data - Sreejit, Ashok | Did not incorporate into CCF; Customer choice | Moderate
GUI\GuiCommon | ICCFGuiCustomizer.cs | Added interface ICCFPanelCustomizer | Did not incorporate into CCF; Customer choice | Moderate
GUI\GuiCommon | ICCFGuiLoader.cs | Added API SetNavigationPanel | Incorporated; Do not maintain override | -
GUI\GuiCommon | INavigationPanel.cs |  | Incorporated; Do not maintain override Customer to reimplement use (due to slight difference in interface definition) | Minor
GUI\GuiScreens | ScreenLoader.cs | Commented out line in CustomizeScreens() to fix the flashing when the OI loads (does not set initial page to Operating Mode) | Do not maintain override; retest | -
GUI\GuiScreens | ScreenLoader.cs | Added HostOverviewScreen to Service screenset | Incorporated HostOverviewScreen to Operations screenset: Customer choice | Minor
GUI\GuiScreens\Screens\Alarms | ActiveAlarmsScreen.cs | Modified ActiveAlarmScreen.cs so that currently selected alarm stays selected even after new alarm arrives | Incorporated; Do not maintain override | -
GUI\GuiScreens\Screens\Service\EquipmentModuleOperatingMode | EquipmentModuleOperatingModeScreen.cs EquipmentModuleOperatingModeScreen.Designer.cs | Added Shutdown, Idle, Standby buttons and PM State text display | Reapply | Minor
GUI\OIClient\OIClient | OIClientConfig.cs | GetChildBranchNames added | Incorporated; Do not maintain override | -
GUI\OIServer\OIServer | OIServer.cs | GetChildBranchNames added | Incorporated; Do not maintain override | -
GUI\OperatorInterface | GuiLoader.cs | Added API SetNavigationPanel | Incorporated; Do not maintain override | -
GUI\OperatorInterface | OIMain.cs | Uses INavigationPanel, uses ICCFPanelCustomizer, customizes Title Panel Checks AutoLogin config parameter | Customer choice: Did not incorporate ICCFPanelCustomizer, or AutoLogin config parameter | Moderate
MaterialTracking | MaterialTrackingServer.cs | Attempts to fix SetMaterialProcessingState | Customer change - use Substrate.SetProcessingState, Substrate.SetTransportState | Moderate
MaterialTracking | Material.cs | Allows ProcessingState to be copied in the copy constructor. | Incorporated; Do not maintain override. TransportState and ProcessingState are now attributes. | -
MaterialTracking | IMaterial.cs | Adds ProcessingState property to interface | IMaterial was removed from package | -
Platform\Brooks\BrooksM2Quad\BrooksM2Quad\Modules | ActiveDualChamberDualSlotLoadlock.cs | Wanted a command completion callback. | Reapply | Minor
Schedulers\Scheduler\Scheduler | Scheduler.cs | Start method short-circuits if already alive | Reapply | Minor
Schedulers\StockQuadScheduler\StockQuadWorkItems | SimCommandProxy.cx | Wanted a command completion callback. | Reapply | Minor
Users\Users | Group.cs | Set the default timeout for Group to 0 minutes instead of 100 minutes | Reapply | Minor
Veeco classes which are copies of CCF classes | Compare To File in CCF 3.6.1 |  | Upkeep with CCF classes may be desired
RedBullScreen RouteRecipeEditorScreen | GUI\GuiScreens\Screens\Recipes\RouteRecipeEditorScreen.cs |  | Possibly merge the bug fix to buttonInsertStep_Click(). | Minor
RedBullScreens\Controls\ModuleStatusViewer | GUI\GuiScreens\Screens\Systems\SystemOverview\ModuleStatusViewer.cs |  | General improvements | Minor
AsciiSerialConnection.cs | IO\IO\Serial\AsciiSerialConnection.cs |  | Dispose was made virtual | Minor
ComPortSerialConnection.cs | IO\IO\Serial\ComPortSerialConnection.cs |  | General improvements | Minor
SerialConnection.cs | IO\IO\Serial\SerialConnection.cs |  | Allows for Reconnecting state | Minor
TcpSocketSerialConnection.cs | IO\IO\Serial\TcpSocketSerialConnection.cs |  | General improvements | Minor
ModbusTCP_Master.cs | IO\IOProvider_Modbus_TCP\ModbusTCP_Master.cs |  | General improvements | Minor

## 3. Release Notes 3.5-3.6.1
This Tab describes the impact to Veeco RedBull due to the features/fixes/changes to CCF since release 3.4, and provides a rough estimate of the effort. The entries are provided in the order given in the CCF Release Notes document for releases 3.5, 3.6, and 3.6.1. However, an actual order for performing the work is not prescribed.
CCF Release Notes from Versions 3.5 through 3.6.1
Version | Release Note Description | Impact to Veeco | Effort?
3.5
3.5 - 1 | Component has a new method RegisterConfigurationParameters for use by derived classes to register all their configuration parameters | No impact to existing code; new feature is available to use | Optional
3.5 - 2 | ConfigurationParameters have two new fields GroupSettable and GroupVisible. These are set in the Cimetrix.ConfigurationEditor.exe and used in the OI configuration screen | Screen improvement, no impact to existing code | -
3.5 - 3 | DataListView control has a new API AddNumericParameter that allows you to specify the format string to use when printing the value. It takes a complete format string, e.g. "{0:F2}" or "{0:D} msec" as used in String.Format(). | New API could be used as alternate to VtmTransforms.PressureWIthUnits, on: AtmosphericRobotServiceScreen, VacuumChamberServiceScreen, VaccumRobotServiceScreen | Optional
3.5 - 4 | EquipmentControlSystem has a new method DisposeOfEquipmentComponents that should be implemented to correctly dispose of any created modules, etc. that implement Idisposable | Recommend implementation in RedBullEquipmentControlSystem | Minor | Steve |  | NOT STARTED
3.5 - 5 | DataItem base class added to FactoryAutomation to contain common properties for Events and Variables. New properties allow code to specify the parent module in the model for dynamic data/event publication rather than having the parameter name parsed to determine the module. Parameter and event names should now contain what is to be published, i.e. State or Pressure, not LL1.VacSys.Pressure. The new module property should contain the module name, LL1.VacSys in the prior example. All components have been updated. This has removed the need for CxFactoryAutomationServer in Supervisor solutions | Modify all calls to CreateEvent, CreateStatusVariable and CreateDataVariable, and new Event, new StatusVariable, new DataVariable. Note, RedBull defines an unrelated DataItem | Moderate | Manu | Changed the signature ofaffected methods | DONE
3.5 - 6 | GEM RemoteCommands were refactored to allow the Notification command to specify the return code | None; GEM not in use
3.5 - 7 | A post-build step has been added to the ConfigurationEditor project to encrypt ConfigDecrypted.xml into Config.xml. Cimetrix now maintains ConfigDecrypted.xml instead of Config.xml. ConfigDecrypted.xml is plain xml so it is possible to compare versions of the file in a revision control system | Customers can choose to version control a decrypted copy of Config.xml (as ConfigDecrypted.xml). Customers could similarly add a post-build step to their automated build to invoke the batch file ccf/Source/Shared/ConfigurationFileEncrypt.bat to generate the encrypted format as Config.xml. | Optional
3.5 - 8 | The CIM300 callbacks have been made extendable. Override one of the CIMXXXCallbackHandler classes you wish to customize, or implement the CIM300 callback interfaces then override CIM300Services.GetXXXCallbackHandler to inject your class | None; GEM not in use | -
3.5 - 9 | A new Service screen has been added to adjust CIM300 and CIMConnect logging levels to help diagnose Factory Automation problems | None; GEM not in use | -
3.5 - 10 | Wafer cycling has been modified to work better for load ports with no CID reader. It will no longer prompt the operator for the carrier ID after the first cycle | None | -
3.5 - 11 | LightTower, MFC, and ThrottleValve have all been refactored and unit tests created for them | No impact to existing code; RedBull defines its own classes | -
3.5 - 12 | The configuration helper classes in Equipment/Components/Configuration have been marked obsolete and will be deleted in a future release of the product. The few classes (MFC, ThrottleValve, LightTower and Brooks vacuum systems) that used the obsolete classes have been modified | None | -
3.5 - 13 | CxFactoryAutomationServer has been removed from the Supervisor solutions, SupervisoryInit template and labs as it is no longer needed | GalaxySMC\Supervisor::StartFactoryAutomation creates a CxFactoryAutomationServer. GalaxySMC\CxFactoryAutomationServer should subclass CimPortalDataService to override GetParentLocator; also replace '.' for '/'. In App.config, remove CxFactoryAutomationServer, add FactoryAutomationServer. | Moderate | Steve | What is meant by subclass? I cant derive it form two classes and so I can not overriode GetParentLocator. | on hold
3.5 - 14 | A new E84Handler class has been added to the Equipment project to handle E84 logic for automated transfers at load ports. The Equipment LoadPort class has been modified to use the E84Handler. The FactoryAutomation LoadPort class has had its E84 logic removed. The VS2008 LoadPort template has been updated. Custom E84 logic is now easier to incorporate by subclassing E84Handler or implementing IE84Handler in a custom class and passing it into the Equipment LoadPort constructor | Did not find RedBull code implementing E84 | -
3.5 - 15 | FactoryAutomationServer has been changed to use the WcfServer generic from Cimetrix.Library. | None | -
3.5 - 16 | FactoryAutomationClientService has been changed to use the WcfClient generic from Cimetrix.Library. | None | -
3.5 - 17 | FactoryAutomationClient has been changed to use the ServiceLocator generic from Cimetrix.Library. | Note several APIs were moved to DataClient. API's SetEpt* renamed to Ept*, search for callers of SetEpt*() in RedBullModule.cs | Minor | Manu | Renamed SEtEpt method to EPT in RedbuullModule.cs | Done
3.5 - 18 | The VTM node has been removed from ToolSupervisorIOConfiguration.xml | Veeco version of ToolSupervisorIOConfiguration.xml is entirely different. Veeco has the file ToolSupervisorSimIOConfiguration.xml exactly and should be updated similarly; unclear if this file is in use. | Minor | Banu/Hao |  | NOT STARTED
3.5 - 19 | The VTM node has been removed from RorzeSimulatedTool.xml | None | -
3.5 - 20 | BroadcastControl.SetValue has been fixed to handle any value type for change detection | AFIServiceScreen has commented-out references | -
3.5 - 21 | The Live Data Graph screen has been modified to only show numeric parameters in the treeview | Screen improvement, no impact to existing code | -
3.5 - 22 | EnableReportsInCIMStore() has been moved after DeployDataModels in all the Supervisor classes so CIMStore report activation will not fail due to missing variables and events. | GalaxySMC.Supervisor already corrected. | -
3.5 - 23 | The AlarmHelper has been removed from FactoryAutomation.LoadPort as unnecessary code. The LoadPort has been modified to use the standard alarm creation methods. | None | -
3.5 - 24 | A bug in the IDAssignments save/restore of the item id assignments has been fixed. It was not saving the module information correctly so it now saves 3 columns: id, module, variable name. The old 2 column (id, path) files will be read and converted on startup. | Formatting of Shared\*Assignments.txt files will be altered due to this code change, customers would want to compare the files before/after the reformatting, to validate that the module information has been added. | Minor | Banu |  | NOT STARTED
3.5 - 25 | The DatabaseLogSink now creates the logging table in the database if it does not already exist, thus eliminating the manual step that was required. | The logging table does not need to be created by a custom script, and it is no longer created by the CCF Installation Assistant; the creation function was added to the Cimetrix DatabaseLogSink library code. No impact to Veeco is expected. | -
3.5 - 26 | The assemblies from the Cimetrix Common package were updated to version 1.13.7.1160 | No | -
3.5 - 27 | Several component states are now published as unique variables instead of them all having the name State. The new variable names are: PumpState, ValveState, VGState, ModuleState and ComponentState. All the OI screens have been updated. This was done because, for example, a Pump is a Component and publishes both ComponentState and PumpState which wasn't possible before. | Consider making unique State variables in AtmosphericRobotScreen, VTM\LoadLockServiceScreen (e.g. Door.State -> Door.ValveState); Check for Null values in OI Screen Update methods | Moderate | Mega
3.5 - 28 | The default model has been modified to remove the VTM and EFEM collection nodes, flattening the hierarchy and simplifying the model and data publication. The OI screens have been updated. The corresponding default CIMStore reports for the Pump and Vent Curves for the load locks have been modified. You can delete the old requests and data using CIMStore Manager and then update the CIMStore definitions using the Installation Assistant. Old data will no longer be available unless you migrate it yourself. | Veeco could be affected by model changes, if they use CCF OI screens that rely on VTM or EFEM parameters. Veeco should compare their EquipmentModel with new verion of the CCF file ccf\Source\EquipmentModels\CIMPortal Model\Equipment.xml. Areas of concern: EFEM components Aligner, EFEMRobot, LP1. May affect GalaxySMC\CxFactoryAutomationServer.cs. Veeco is not expected to be impacted by the change to the Pump and Vent Curves. | Moderate | Banu
3.5 - 29 | The Equipment LoadPort class has been modified to use the new E84Handler class. Any custom load port drivers will need to be updated for the new constructor signature. | Modify RedbullLoadPort | Moderate | Not found the usage : Banu, Please confirm
3.5 - 30 | The CxThreadPoolQueue ActionItem delegate definition has been removed. The C# System.Action<T> is now used. | None | -
3.5 - 31 | The FactoryAutomationClient RemoteCommand class was changed to use a List instead of a Dictionary for its parameters. It was also updated to use the .NET CxValue package instead of the COM CxValue objects. | None | -
3.5 - 32 | Material Tracking has been refactored for extensibility and usability. As part of this effort, the MaterialTracking server now contains the "master" information for all defined material and locations. The refactoring has resulted in the following breaking changes
3.5 - 33 | The MaterialTracking Substrate class has been replaced with a static class for use in accessing attributes on a Material object. In most cases, use a Material instead of a Subtrate for instances, then use the static Substrate class to access the Material's attributes. | Investigate use of Substrate to be replaced by Material. Replace Material.ProcessingState with Substrate.GetProcessingState(), in area of RedBullScheduler. Modify for use of custom attributes, e.g. new API SetAndSendAttribute<T>() | Moderate | done
3.5 - 34 | The MaterialTracking Carrier class has been replaced with a static class for use in accessing attribute on a Container object. In most cases, use a Container instead of a Carrier for instances, then use the static Carrier class to access the Container's attributes. | Veeco does not appear to use Carrier | -
3.5 - 35 | The IMaterial and IMaterialLocation interfaces have been removed. Use Material and MaterialLocation classes instead. | Modify uses of Wafer.Material property in LoadLockServiceScreen, VacuumRobotServiceScreen. Search for uses of IMaterial in RedBull.TransportModules LoadLock, VacuumChamber, etc. Search for uses of IMaterialLocation. Investigate use of Container. Search for uses of GetLocation, GetLocations, GetMaterial. | Moderate | Done
3.5 - 36 | The SetMaterialTransportState, SetMaterialProcessingState, and PlaceUnknownSubstrateInCarrier methods were removed from the IMaterialTrackingClientService interface. Use Substrate.SetTransportState, Substrate.SetProcessingState, and IMaterialTrackingClientService.AddMaterial methods instead. | Replace old APIs in SchedulerTests\StubMaterialTracker | Minor | Mega |  | on hold
3.5 - 37 | The MaterialProcessingStateChanged and MaterialTransportStateChanged events were removed from the IMaterialTrackingClientService interface. Use the MaterialAttributeChanged event instead. | Recommend use of custom attributes | Optional
3.5 - 38 | In IModule and Module, GetMaterialLocations has been renamed to GetMaterialLocationNames, and now only returns the material location names. If the MaterialLocation is needed, it must be retrieved from the MaterialTracking server. | Replace use of GetMaterialLocations with GetMaterialLocationNames. Investigate cases where retrieving MaterialLocations from the Material Tracking Server is needed. | Moderate | Need to cehck with Change in Redbull Module- else it is done.
3.5 - 39 | IProcessModule and ProcessModule have been modified to use the Material class instead of IMaterial. | No impact to existing code; cursory use of IProcessModule | -
3.5 - 40 | IFALoadPortCallback interface was modified to eliminate obsolete methods and parameters. Custom classes implementing this interface will need to be updated (this is not common, unless the CCF Equipment LoadPort class is not being used.). | None; IFALoadPortCallback not in use | -
3.6
3.6 - 1 | The navigation panel on the OperatorInterface GUI can now be customized. Customers may implement the new interface INavigationPanel and call the GUILoader method SetNavigationPanel. | RedBullScreens CustomTitlepanel affected, NavigationScreen affected by minor differences in CCF INaviationScreen APIs | Minor | Manu | Moved SetNavigationPanel from CustomTitlePanel to CustomizeAppearanec Method in Guicustsomize.cs | Done
3.6 - 2 | IWidget now has an additional public interface GetValue which returns the last set value. This interface method is now implemented by the CCF classes for UI controls. Custom controls implementing IWidget should also implement this method. | None | -
3.6 - 3 | Recipe uploads and downloads can now specify a folder. Previously the Production folder was the only target folder allowed. Now Production subfolders or Engineering subfolders are allowed. | Screen improvement, no impact to existing code | -
3.6 - 4 | The Material Movement screen allows Material attributes to be edited if a Material is created using this screen. | AFIServiceScreen appears to be a copy of EFEMServiceScreen but is entirely commented out. | -
3.6 - 5 | Functionality to handle Wafer and Wafers controls has been added to BaseScreen. Custom screens derived from BaseScreen may add Wafer and Wafers controls that will be automatically updated by Material Tracking information; the screens would no longer need to store MaterialLocations or subscribe to the OIClient LocationMapChangedEvent. | Screens may be improved: AtmosphericRobotServiceScreen, LoadLockServiceScreen, VacuumRobotServiceScreen. AFIServiceScreen appears to be a copy of EFEMServiceScreen but is entirely commented out. | Moderate | We can not do this as we have WPF screens
3.6 - 6 | Data publishing now allows use of null values. Null values are the equivalent of 0-length data items in GEM data. The CCF base screen class was corrected to permit such values. Custom screens have responsibility to check for null values when processing data updates to their controls | Recommend implementing null checks, likely affecting publication of State variables. | Minor | Ashok |  | NOT STARTED
3.6 - 7 | CCF has been updated to use CIMConnect 1.12.7, CIM300 1.13.9 and CIMPortal 1.2.8
3.6 - 8 | In the OperatorInterface (OI), the startup sequence has been changed so custom colors take effect before any screen elements are created. The SetTitlePanel method has been moved from the ICCFScreenCustomizer interface to the ICCFAppearanceCustomizer and should now be called in the CustomizeAppearance method call. This change allows the OI to use the desired title panel from the beginning. Overall, these changes have reduced the OI startup time and removed the visual jarring that occurred when the custom color and title panel changes were applied. | RedBullScreens CustomTitlepanel affected | Minor | Manu | Removed CustomeTitlePanel calss from GuiCustomizer.cs And moved SetTitlePanel and SetNavigationPanel to CustomizeAppearance Method. | Done
3.6 - 9 | DatabaseWaferHistory, DatabaseEPTHistory, and DatabaseAlarmHistory now use the ServiceLocator pattern which allows for supplying a new provider. Customers may override the GetProvider method to support a different database type. | GalaxySMC\Supervisor method StartAlarms() possibly affected by App.config settings, compare to CCF ToolSupervisor | Minor | Ashok/Steve |  | NOT STARTED
3.6 - 10 | On the OperatingMode screen, the Initialize Equipment and Initialize Module buttons are separately localized and updated for the language translation to better fit the buttons. | Screen improvement, no impact to existing code | -
3.6 - 11 | Reworked the Equipment LoadPort class, redefining protected access for increased extensibility. Added a virtual method to allow customers to set custom attributes on material. | Investigate RedbullLoadPort | Minor | NA |  | NA
3.6 - 12 | ICxE87Callback5 interface was removed from CIM87CallbackHandler because it was not used in standard CCF product code. Customers who want to use the interface should implement it in a custom subclass of Cim87CallbackHandler. | None, E87 not in use | -
3.6 - 13 | The Alarms package removed a restriction limiting alarm codes to 1-8 (based on E5 standard); it now allows any byte. This supports the definition of custom alarm codes in multiple application deployments. | None, AlarmCode not in use | -
3.6 - 14 | Midas data variable creation was corrected so that the module name is not prepended to the name. | None, MidasModule not in use | -
3.6 - 15 | Active Alarm screen was modified to reduce flickering during updates. | Screen improvement, no impact to existing code | -
3.6 - 16 | The Labs are no longer installed by the CCF installer. | None. Labs may be downloaded from the Cimetrix Support Website | -
3.6 - 17 | The sample RorzeEquipmentControlSystem was modified to reject simultaneous Initialize Equipment commands. | None, RorzeEquipmentControlSystem not in use | -
3.6 - 18 | A change was made to prevent an exception while publishing jobs information. Occasionally an exception "Collection was modified; enumeration operation may not execute" would occur. The FactoryAutomation package was changed to avoid problems passing jobs data. | None | -
3.6 - 19 | MaterialTracking used to allow creation of a material with a name that already exists. It no longer allows duplicate material names. | None | -
3.6 - 20 | The User Management screen was reworked to improve ease-of-use. A single tree view of Functions and Screens is displayed for the User or Group selected. A color key for User, Group, or available (unselected) is shown. Changes to Group permissions automatically update the applicable User permissions. | Screen improvement, no impact to existing code | -
3.6 - 21 | The default Administrative user sysadmin is no longer required and may be deleted once another user has been given Administrator privileges. The system will ensure that there is always at least one user with Administrator privileges and will recreate sysadmin if needed. Also, passwords are not allowed to expire for any user that is a member of the Administrator group. | Screen improvement, no impact to existing code | -
3.6 - 22 | Fixed a problem on the LightTowerConfiguration screen which caused it to acquire a UserEditSession. | Screen improvement, no impact to existing code | -
3.6 - 23 | The look of GradientButton and PushButtons was changed to improve differentiation between the enabled and disabled states. | Observe change in look of controls derived from GradientButton | Minor | NA |  | NA
3.6 - 24 | DatabaseLogSink configuration was changed, affecting CCF Supervisor classes. The default persistence for log records has been changed. Previously, ChangeRecord, Warning, and Error records were kept forever. Now they are are persisted for a default of 180 days, consistent with History records. Also, a default message persistence of 30 days was added. Custom supervisor class implementations may need to modify the StartLogging method and the App.config file in the Database Persistence Configuration section; refer to the CCF class ToolSupervisor for examples | Compare uses of DatabaseLogSink (DBSupervisor, VeecoStoreInterface, GalaxySMC Supervisor) with example in CCF ToolSupervisor.StartLogging() for applicable changes. | Minor | Ashok/Steve |  | NOT STARTED
3.6 - 25 | DataPublication has been moved out of FactoryAutomation and into its own package, Data. To publish event and variables, a reference to the Cimetrix.DataClient.dll will be needed. The DataServer should be hosted in the same application as the FactoryAutomationServer. Customers may need to adjust their code to these changes: | Update VS project References with Cimetrix.Data. See the following rows. | Moderate | Done
3.6 - 26 | The following methods have been moved from FactoryAutomationClientService and are now located on DataClientService:
3.6 - 27 | SetVariables | Yes, uses found of this API |  | Done
3.6 - 28 | SetVariable | Yes, uses found of this API |  | Done
3.6 - 29 | TriggerEvent | Yes, uses found of this API |  | Done
3.6 - 30 | RegisterVariables | Yes, uses found of this API |  | Done
3.6 - 31 | RegisterEvents | Yes, uses found of this API |  | Done
3.6 - 32 | GetIdFromName | None, no uses found of this API |  | NO
3.6 - 33 | IsIdMapReady | None, no uses found of this API |  | NO
3.6 - 34 | The NameToIdMapReady event has been moved from FactoryAutomationClientService and is now located on DataClientService. | None, no uses found of this event |  | NO
3.6 - 35 | The following classes have been moved to the Cimetrix.CimControlFramework.Data namespace:
3.6 - 36 | DataItem | no; RedBull defines an unrelated DataItem |  | No
3.6 - 37 | DataType | Yes, uses found of this class |  | Done
3.6 - 38 | DataVariable | Yes, uses found of this class |  | Done
3.6 - 39 | Event | Yes, uses found of this class |  | done
3.6 - 40 | StatusVariable | Yes, uses found of this class |  | Done
3.6 - 41 | Variable | Yes, uses found of this class |  | Done
3.6 - 42 | VariableType | None, no uses found of this API
3.6 - 43 | If the application is out-of-process from the DataServer, an entry for the WCF connection to the DataServer should be added. | Compare GalaxySMC\App.config with ToolSupervisor\App.config | Minor | Manu |  | Done
3.6 - 44 | Applications hosting the FactoryAutomationServer should be modified to create the DataServer. | GalaxySMC\Supervisor.StartFactoryAutomation() needs to instantiate the CimPortalDataService | Minor | Ashok/Steve |  | NOT STARTED
3.6 - 45 | The DeployModels method has been moved from the FactoryAutomationServer to the DataClient and renamed DeployModel | GalaxySMC\Supervisor affected, replace call faServer.DeployDataModels with DataClient.Server.DeployModel | Minor | Manu | Modified Supervisor.cs for this | Done
3.6 - 46 | As a result of the new Data package, some classes in the CimStoreData package were renamed to have CimStore prefixes. These changes mainly affected OIServer and OIClient. These changes are internal to the product and are not expected to affect customers. | Replace CIMStoreData.IDataServer with Data.IDataServer in RedBullScreens\Galaxy.OperatorInterface.exe.config | Minor | Manu | Changed RedBullScreens\Galaxy.OperatorInterface.exe.config | Done
3.6 - 47 | The Monitor package was changed to use the Data package instead of CIMPortal for trace and event requests. As a result, it may be necessary to redefine existing monitors. Also, not all events and variables available from CIMPortal are available from the Data package. | Veeco is not expected to be impacted | -
3.6 - 48 | The CCF GUI components were changed to use the Data package instead of CIMPortal data requests. Instead of using CIMPortal locator strings to associate CIMPortal parameters to CCF GUI controls, CCF variable names are used. Generally, this means the '/' character should be replaced with a '.' character. Customers should search their screen classes to make changes, such as in calls to BaseScreen.AddControlToCollection | RedBullCommons.LocatorPath affected RedBullScreens, several classes affected. RedBullScreens\Controls\ModuleStatusViewerSpec.cs is a copy from CCF 3.4; examine to merge changes. | Moderate | Done ( Removed ModuleStatusViewer as it is not used)
3.6 - 49 | Some CCF GUI component method and variable names were changed. In general, "locator" was changed to "variable name" and "parameter" was changed to "variable". Most of these changes are internal to CCF; however, some of them affect the public interfaces. Customers may need to adjust their code to these changes:
3.6 - 50 | The DataParameter class was renamed to VariableInformation. | Use of DataParameter in MainPageViewModelWPF.cs, BreadCrumbModel.cs | Minor | Ashok | Need help to understand the implementation logic | ON HOLD
3.6 - 51 | The ParameterType property was renamed to DataType and the type was changed from string to DataType
3.6 - 52 | The Locator property was renamed to Name
3.6 - 53 | OIClient
3.6 - 54 | GetParameterList method was renamed to GetVariableList | Use of GetParameterList in MainPageViewModelWPF.cs, BreadCrumbModel.cs | Minor | Ashok | Need help to understand the implementation logic | ON HOLD
3.6 - 55 | Base Screen class
3.6 - 56 | The DataParameters property was renamed to Variables | None, no uses found | -
3.6 - 57 | The GetAllDataParameters method was renamed to GetAllVariables | None, no uses found | -
3.6 - 58 | The GetNodeDataParameters method was renamed to GetNodeVariables | None, no uses found | -
3.6 - 59 | The GetAllChildDataParameters method was renamed to GetAllChildVariables | None, no uses found | -
3.6 - 60 | The GetDesiredLocatorStrings method was renamed to GetDesiredVariableNames | In RedBullScreens, current uses are commented out | -
3.6 - 61 | IAdvancedWidget interface
3.6 - 62 | GetSubscriptionLocators method was renamed to GetSubscriptionVariableNames | Search for overrides of IAdvancedWidget.GetSubscriptionLocators Note, Veeco has own implementation of GetSubscriptionLocators in several classes that are not directly affected. Also affected are methods ShouldSubscribeForVariables in RedBullOIInterfaceUnitTests. | Moderate | Done
3.6 - 63 | DataListView class
3.6 - 64 | Add*Parameter methods were renamed to Add*Variable | RedBullScreens affected: AtmosphericRobotServiceScreen, VacuumChamberServiceScreen, VaccumRobotServiceScreen | Minor | Manu | Renamed AddPArameter method with AddVariable methods in the affected files | Done
3.6 - 65 | ClearPameters method was renamed to ClearVariables | None, no uses found | -
3.6 - 66 | ParameterTreeView class was renamed to VariableTreeView | None, no uses found | -
3.6 - 67 | In the Factory Automation package, the CCRuleEvaluator class was renamed DataRuleEvaluator. DataRuleEvaluator now uses the Data package instead of CIMConnect. This primarily affects the LightTower class. As a result, some of the LightTower condition variable names will need to be updated in the rules defined in the configuration file. Customers should compare their equipment configuration file with the CCF default file in C:\ccf\Source\Shared\Config.xml in the FactoryAutomation/LightTowerConditions branch; the entries for Value and FactoryDefault for several conditions must be edited as follows | Edits needed to Veeco's Config.xml for Light Tower conditions | Minor | STEVE | NA | NA
3.6 - 68 | The 'ALARMSSET' variable should be replaced with 'NumActiveAlarms'.
3.6 - 69 | The 'CONTROLSTATE' variable should be replaced with 'GemControlState'
3.6 - 70 | The 'PROCESSSTATE' variable should be replaced with 'GemProcessingState'
3.6 - 71 | Supervisor configuration parameters for CIMStore were moved from the Configuration package to the app settings file. This change enables support of multiple CIMStore database types, and is consistent with other CIMStore configuration and Database history configuration parameters. In the configuration file, the parameters under the "ToolSupervisor/Database" branch were deleted: LoggingEnabled and TableSpace were obsoleted; Provider, UserID, Password, and ServerName were combined into a single CIMStoreSQLServerCfg app setting. Refer to the CCF class ToolSupervisor. | GalaxySMC.Supervisor class implements EnableEquipmentInCIMStore, reads custom entries from Config.xml for their database, they may not use Cimetrix changes. Verify for no impact | Minor | Manu | Not Affected | Done
3.6 - 72 | Customers should compare their equipment configuration file with the CCF default file (C:\ccf\Source\Shared\Config.xml) and remove the "ToolSupervisor/Database" branch. | Optional | Minor | Manu | These are not needed as of now | Future
3.6 - 73 | Custom supervisor class implementations may need to modify the EnableEquipmentInCIMStore method. | Optional | Minor | Manu/Ashok | These are not needed as of now | Future
3.6 - 74 | In the supervisor App.config file insert a setting for "CIMStoreSQLServerCfg" equivalent to "MYSQL;localhost:3306;ccfuser;ccfpwd". | Optional | Minor | Manu/Ashok | These are not needed as of now | Future
3.6 - 75 | The Factory Automation package was refactored for added extensibility.
3.6 - 76 | CimConnectServices and Cim300Services now allow for customized host interface behavior. Customers may provide alternate implementations for these services or their callback handlers. Refer to the CCF Developer Guide, sections 3.3.6.4 - 3.3.6.6 for examples. | None, GEM not in use | -
3.6 - 77 | The constructor for Cim300Services has been reduced to just initialize fields and properties. Other functionality has been moved to the Initialize method. Custom versions should make similar modifications. | None, GEM not in use | -
3.6 - 78 | Two fields in FactoryAutomationServer which cached CimConnectServices.Instance and Cim300Services.Instance have been removed. Callers may access the Instances from the Services directly. | None, GEM not in use | -
3.6 - 79 | The GetCim*CallbackHandler methods have been removed and replaced with Cim*CallbackHandler properties. This change allows the use of custom callback handlers without requiring a custom Cim300Services class. Customer code using GetCim*CallbackHandler methods should make similar modifications. | None, GEM not in use | -
3.6 - 80 | CIM*CallbackHandler classes were renamed to Cim*CallbackHandler to match the CCF Style Guide and other CCF classes. Customer code should make similar renamings. | None, GEM not in use | -
3.6 - 81 | The GemServiceLocator has been deleted, its functionality is replaced by CimConnectServices.Instance. Customer code with references to GemServiceLocator should use CimConnectServices.Instance instead. | None, GEM not in use | -
3.6 - 82 | An Initialize method was added to the FactoryAutomationServer and should be called immediately after instantiation. Custom supervisor class implementations may need to be modified to call Initialize during the StartFactoryAutomation method; refer to the SampleSupervisor class for an example. | GalaxySMC\Supervisor.StartFactoryAutomation() needs to call FactoryAutomationServer.Initialize. | Minor | Manu | Chnaged the code to be in sync with sample supervisor. | Done
3.6 - 83 | FactoryAutomationServer CreateLoadPort has been removed. Customer code that overrode or called this method should change to Cim300Services CreateLoadPort instead. | None, no uses of CreateLoadPort | -
3.6 - 84 | Changed when Alarms are set in the GEM host. Previously, any alarm enabled for host reporting would be set in the GEM host upon the posting the alarm to the Alarm Server. Now, two additional conditions apply. The first condition is when the scheduler is ready for jobs (when the equipment is in Jobs mode). The second condition is when the configuration parameter "FactoryAutomation.SetAlarmsWhenNotReadyForJob" is set to true. If either condition is true, the GEM host will be notified. SetAlarmsWhenNotReadyForJob is a new dynamic configuration parameter, whose default value is false. If original behavior is desired, customers should set SetAlarmsWhenNotReadyForJob to true. | Add configuration parameter "SetAlarmsWhenNotReadyForJobs" with appropriate default in FactoryAutomation section of Config.xml. | Minor | Manu/Banu |  | NOT STARTED
3.6 - 85 | During Event construction, all Data Variable names must now include the component name in order to be full-path names. Custom subclasses of Component which use the CreateEvent method do not need to be modified, as the CreateEvent method will automatically add the component name. Custom code directly calling the Event constructor method may need to be changed. | Look for callers of new Event() | Minor | Manu | changed the signature of events found | Done
3.6 - 86 | CimStoreDataServer now uses the ServiceLocator pattern which allows for supplying a new provider. This change primarily affects the OIServer internal to the product. Custom supervisor class implementations may need to set the OIServer CimStoreDataServer property in the StartOIServer method; refer to the SampleSupervisor class for an example | In GalaxySMC\Supervisor, in StartOIServer(), create the CimStoreDataServer. Replace CIMStore* with CimStore* in GalaxySMC\App.config. | Minor | Manu/Ashok | Done with the changes in Supervisor. Check with Ashok for App.config changes | HOLD
3.6 - 87 | The relationship between ActiveObject and Component has been changed from inheritance to composition. Customers who wish to replace ActiveObject functionality in Component can now do so at run time instead of recompiling the Common and Equipment packages. Backwards compatiblilty has been maintained as much as possible. Customer code may change in the following conditions: | RedBullSupport.SimpleActiveObject should implement Iinvoker | Moderate | Refactor it - Get rid of it
3.6 - 88 | For classes which derive from ActiveObject but not Component
3.6 - 89 | There is no longer an abstract ServiceState method. If a ServiceState method is needed, customers should set the invoker ServiceState delegate. | SimpleActiveObject affected. Veeco copy of VGCCommProvider: must delete ServiceState(), otherwise merge optional | Minor | Senthil
3.6 - 90 | The EnqueueCommand methods were moved from ActiveObject to Component. Custom subclasses of ActiveObject should be changed to call the Submit method instead. | None | -
3.6 - 91 | For classes which derive from Component
3.6 - 92 | The ThreadEvent property is not available in the constructor. This will affect customer code that defines IO groups and uses the ThreadEvent property in the constructor method. Customers should create an override of the ConfigureIO method from which to refer to the ThreadEvent property. | Some RedBullEquipment Component classes affected | Minor | Manu | I could see that startIO() is called from the constructor which uses the ThreadEvent. I would like move this Call to StartIO() method to ConfigureIO() . Change will be done on the following components. 1. SpindleMotor.cs 2. BGM.cs 3. DIOBLock.cs 4. Barathron.cs 5. MassFlowController.cs 6. LeyboldProcessPump.cs 7. ThrottleValve.cs 8. SafetyController.cs 9. Valve.cs | HOLD
3.6 - 93 | The ProcessCommand method is no longer available to be overridden. Customers should override the delegate methods OnInvokingCommand or OnInvokedCommand, or replace the command invoker. | RedBullComponent should not implement ProcessCommand | Minor | Manu | Removed ProcessCommand and Service Commands from RedbullComponent.cs and Added OnInvokedCommand() method. | Done
3.6 - 94 | The Run and ServiceCommands methods are no longer available to be overridden. If customer code has overridden these methods, it should be modified to entirely replace the command invoker. | RedBullTransportModule classes should not implement ServiceCommands() | Minor | Mega | Found that it is overridden at 4 places. The code inside these methods need to be removed.
3.6 - 95 | Calls to the Start method have been removed from the constructors for CCF Components. When using CCF Components, the Start method must now be explicitly called after creation (usually immediately after). The Start method was also added to the IComponent interface. Custom subclass constructor methods, and their callers, including unit tests, should be examined to determine if calls to Start must be moved or added | May have no change. RedBullComponent is directly derived from Component; (not many CCF components are directly used) GalaxySMC.Supervisor does call Start on the ECS | Minor | Manu | NO changes are needed | Done
3.6 - 96 | In the Factory Automation package, methods used to update Module Process Tracking state were improved for efficiency. The signature of the methods MPTExecutionStarted and MPTExecutionStarted2 on the IFactoryAutomationClientService and IFactoryAutomationServer interfaces were affected. The interfaces now use a CxValue parameter, replacing a CxValueObject parameter. CxValue is preferred over CxValueObject because it is a native .NET implementation; subsequently it is converted to a byte array preferred when potentially going across a WCF connection. In the CCF class ProcessModule, the method PerformProcess implements the new signature on MPTExecutionStarted, replacing the prior (CCF 3.5) implementation in the Process Module method PrePerformProcess. Custom subclasses of ProcessModule, and other callers of MPTExecutionStarted or MPTExecutionStarted2 may need to be changed to conform to the new interfaces. | None, no uses found | -
3.6 - 97 | The ProcessModule base class was updated to use the Action->PerformAction->DoAction pattern. The two methods affected are PerformPrepareForRecipes and PerformProcess. Custom subclasses of ProcessModule which overrode these two methods should now override DoPrepareForRecipes and DoProcess instead. In the Do* methods, customer code may not need to call SetModuleState because the base class has done this in the Perform* methods. | None, no uses found | -
3.6 - 98 | The Valve base class was updated to use the Action->PerformAction->DoAction pattern. The CommandValveOpen method was renamed to be DoOpen. The CommandValveClosed method was renamed to be DoClose. Custom subclasses of Valve which called CommandValveOpen or CommandValveClosed should be changed. | None, no uses found | -
3.6 - 99 | The Aligner base class was updated to use the Action->PerformAction->DoAction pattern. Custom subclasses of Aligner which overrode Perform* methods should now override Do* methods instead. In the Do* methods, customer code may not need to call SetState because the base class has done this in the Perform* methods. | RedBullEquipment WaferAligner class affected | Minor | Manu/Banu |  | NOT STARTED
3.6 - 100 | The LoadLock base class was updated to use the Action->PerformAction->DoAction pattern. Custom subclasses of LoadLock which overrode Perform* methods should now override Do* methods instead. In the Do* methods, customer code may not need to call SetState because the base class has done this in the Perform* methods | None, no uses found | -
3.6.1
3.6.1 - 1 | Midas loadport module was changed not to trigger events related to process module. Midas loadport module was changed to use one set of shared DVs for its events. | None, MidasLoadPort not in use | -
3.6.1 - 2 | Some usages of TryParse API call were replaced by Parse API. This corrected an exception handling error. | Veeco maintains own copy of VGCIOProvider.cs, ModbusTCP_Configuration.cs; optional to keep current with Cimetrix changes | Minor | Banu/Hao |  | NOT STARTED
3.6.1 - 3 | Modbus IO provider was modified to correctly parse the provider name in the case where the name contained a ".p" in the middle. | Veeco maintains a copy of ModbusTCP_IOProvider, examine to merge changes. Optional. | Minor | Senthil |  | NOT STARTED
3.6.1 - 4 | The equipment processing state now changes to Idle when all the wafers in the equipment have been returned to the FOUPs instead of waiting until the FOUPs were removed. This behavior now matches the behavior of CCF 3.4. | None | -
3.6.1 - 5 | The Jobs Overview screen had a defect where it didn’t display a defined process job. This problem has been corrected and it now displays the process job in the "Pooled Process Job" list. | Screen improvement, no impact to existing code | -
3.6.1 - 6 | The criteria to determine that a carrier is ready to start processing a job was changed; "In access" state is no longer used. | None | -
3.6.1 - 7 | A defect on the Wafer Cycling screen was corrected. Previously, cycle parameters for LP1 were applied to other LPs; now values for each LP will be used. | Screen improvement, no impact to existing code | -
3.6.1 - 8 | On the Wafer Cycling screen, the Start, Stop, Pause, and Resume buttons are now enabled or disabled consistent with the state of the wafer cycling job. | Screen improvement, no impact to existing code | -
3.6.1 - 9 | A defect on the Create Process Job screen was corrected. Occasionally an error message was posted when a background thread attempted to update the UI thread | Screen improvement, no impact to existing code | -
3.6.1 - 10 | The IFALoadport interface has been changed to include two new properties and renamed one property. The new properties are CarrierIdStatus and CarrierSlotMapStatus. CarrierIdStatus returns the Carrier ID verification state and CarrierSlotMapStatus returns the Carrier slot map verification state. The LPCarrierAccessingStatus property was renamed to CarrierAccessingStatus. These changes will affect any customer who has implemented IFALoadport interface | None; IFALoadPort used by RedBullLoadPortTest | -
Note on B152: Tami Tracey: I believe the description is in error, the original text of this release note was more accurate: The condition was changed to require that the carrier accessing state is "Not In Access"

## May13-Issues
# | Issue Description | Status | Priority | Owner | Remarks
1 | when OI launches, There is a crash but still all the screens are loaded except automation screens | Fixed |  |  | The issue was in GUICustomizer.cs. Removed some other sreens from the screen set Which are added as a part of CCF3.7
2 | VaccumChamber/slotValves/Slotv;av1/Status -- somewhere"." is missing. | Fixed |  |  | The issue was in slotValve.class..( hardcoded as .Replace("" Fixed other files too
3 | Equipment model does not deploy properly | Fixed |  | Mega | Removed the unused EFEM Subsystem & IDReaderSM StateMachine
4 | No alrams are registered | Fixed |  | Mega | (Depenednt on Deployment of equipment model) Once the equipment model issue was fixed, this got fixed
5 | In PM.cs , exception is caughty because of AppDcim = new CxCCFWCFAppDCIMClient("CcfWcfAppDcimEndpoint"); AppDcim is null when CreateAndStartEquipmentControlSystem(); is called from Sueprvisor | Fixed |  | Steve | Removed this, as it needs to move to Supervisor.
6 | Seeing errors in console : Cannot assign data item " EQP.PM1.MaterialTransferAlarm" an id in range 50000000- 500000999, This id range is fulll' For all the errors in CreateBubblerSlices() in SDA.cs | Fixed |  | Banu | Removed the text files. Even after that this is seen ( NOT SEEN ON 14/5)
7 | EnableEquipmentInCIMStore(); raises a warning, cannot set server configuartion SQLserver : UnknownSQLType | Fixed |  |  | Implemented as per CCF supervisor class
8 | Invalid operation exception in PMC.PM.PM | Fixed |  | Steve | I do not see this issue, so just made it fixed.
9 | Supervisor console errors about missing device in model, GUI Parameter missing in model | Fixed |  | Mega/Manu | Fixed some issues…still some need to be fixed
10 | PM Idle sync failure | Fixed |  | Mega | Code changes to CCF 3.4 to trigger events when the value of status variable is set or changed were missed during merging to CCF 3.7.
11 | Warnings in DB Supervisor | Fixed |  | Ashok/Manu | Replaced '/' with'.' in GetDBContextForTrace(string TracePoint)
12 | Configuration Server warnings in supervisor during startup | Fixed |  | Ashwin
13 | Device Communication Issue | Fixed |  | Ashwin | There is a delay in the way the dat is read from the simulator, only happens the first time, we can work around this for now. Introduced a delay between ScannedIOGroup Start and servicestate calls start
14 | Supervisor errors as warning | Fixed |  | Steve
15 | Material Location Issue: Getting these warnings during startup 2013-05-15T17:24:47.914+05:30 CimPortalDataService Warning Unable to find parent Equipment/VTM/VacuumChamber/Robot/Arm for material location VTM.VacuumChamber.Robot.Arm 2013-05-15T17:24:47.915+05:30 CimPortalDataService Warning Unable to find parent Equipment/VTM/LoadLockA/Shelf1 for material location VTM.LoadLockA.Shelf1 2013-05-15T17:24:47.916+05:30 CimPortalDataService Warning Unable to find parent Equipment/VTM/BufferStation/Shelf1 for material location VTM.BufferStation.Shelf1 2013-05-15T17:24:47.916+05:30 CimPortalDataService Warning Unable to find parent Equipment/VTM/BufferStation/Shelf2 for material location VTM.BufferStation.Shelf2 2013-05-15T17:24:47.916+05:30 CimPortalDataService Warning Unable to find parent Equipment/VTM/BufferStation/Shelf3 for material location VTM.BufferStation.Shelf3 2013-05-15T17:24:47.918+05:30 CimPortalDataService Warning Unable to find parent Equipment/VTM/BufferStation/Shelf4 for material location VTM.BufferStation.Shelf4 2013-05-15T17:24:47.919+05:30 CimPortalDataService Warning Unable to find parent Equipment/MFI/Shelf for material location MFI.Shelf 2013-05-15T17:24:47.922+05:30 CimPortalDataService Warning Unable to find parent Equipment/PM1/L1 for material location PM1.L1 2013-05-15T17:24:47.930+05:30 CimPortalDataService Warning Unable to find parent Equipment/ToolSupervisor for variable ToolSupervisor.ToolSupervisorVersion 2013-05-15T17:24:48.400+05:30 CimPortalDataService Warning Unable to find parent Equipment/PM1/L1 for event WaferStart 2013-05-15T17:24:48.401+05:30 CimPortalDataService Warning Unable to find parent Equipment/PM1/L1 for event WaferEnd 2013-05-15T17:24:48.403+05:30 CimPortalDataService Warning Unable to find parent Equipment/AlarmServer for alarm AlarmServer.PreownedAlarm | Fixed |  | Mega
16 | Gui Parameter Not found errors for vent valves | Fixed |  | Mega
17 | Gui Parameter Not found errors for digital sensors | Fixed |  | Mega
18 | Alarm Message length related warnings in supervisor | Fixed |  | Mega
19 | Merging issue - LogCategory. OperatorAttention is not found | Fixed |  | Ashok
20 | Merging Branch to Trunk | Fixed |  | Manu
21 | Loadlock is not getting initialised | Fixed |  | Mega
22 | Remove the CxCOMReferences and commit the interop DLLs to SVN from the CCF Build so CCF will build on the CI Server | Fixed |  | Steve
16 | Update the CI Server to build CCF 3.7 for the trunk | Fixed |  | Steve | Created another build agent and configured with CCF 3.7. The new build server is SOM-TCBUILD03
24 | Resolve CCF Warnings | Fixed |  | Steve | Relates these to Cimetrix. Some they will fix later but none considered harmful
17 | Warning 1 The event 'Cimetrix.CimControlFramework.Data.Variable.ValueSet' is never used DataClient C:\SVN\Sprint40\Data\DataClient\Variable.cs 95 62 Warning 2 The event 'Cimetrix.CimControlFramework.Data.Variable.ValueChanged' is never used DataClient C:\SVN\Sprint40\Data\DataClient\Variable.cs 100 66 | On Hold |  | Manu | Needs to be looked into, this is Veeco custome and maybe can be removed.
18 | PlaceCarrier command is failing in MFI | Fixed |  | Manu
19 | PM state is not getting displayed in title bar | Fixed |  | Banu
20 | Manual place is not happening | fixed |  | Shruti | component mismatch was preventing the status of the loadlock, robot and carrier presence varaible from updating. Fixed this
21 | GT is not happening - robot arm is not getting updated in simulator. | fixed |  | Shruti
22 | MFI Z-lift up is getting failed from GT is started from MFI | Fixed |  | Ashwin | Explicitly called servicestate as it was not getting called during Zlift movement.
23 | In data viewer tabs are disabled, cannot select any devices | Fixed |  | Ashok | Dependant on Item # 34
24 | Performance Counter logs were coming always saying possible fault for DiskWrite Bytes/sec | Fixed |  | Mega | Increased the range to 500KB in config file. Now the rate is reduced
25 | Fix Failing unit test cases | Fixed |  | Sushma Shree/Impana | Except for one of the test case in StatusVariableWatchdog. It is ignored as of now. Once Megha fixes the issues in StatusVariableWatchdog class.. This can be fixed.
26 | Digital Inputs screen is not getting updated based on the DIO values | Fixed |  | Jayaram
27 | Remove status variable from Trigger Event call and pass a data variable instead | fixed |  | Manu
28 | Sometimes see AppDCIM errors for DeviceCommunicationError for any one of the slice during dynamic model deployment AddDCPObject Failed: a DCP object with the same name PM1.SDA.HydridePanel.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice1.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice2.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice3.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice4.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice5.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice6.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice7.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice8.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.BubblerSlices.Slice9.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.DopantSlices.Slice1.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.DopantSlices.Slice2.DeviceCommunicationAlarm and type already exist AddDCPObject Failed: a DCP object with the same name PM1.SDA.DopantSlices.Slice3.DeviceCommunicationAlarm and type already exist | Under Observation |  | Jayaram | (Steve) I did "some" testing on this and could not reproduce this.
29 | In scheduler screen when software starts up, slot valves remains opened. | Fixed |  | Manu
29 | Group Transfer is not working | Fixed |  | Mega | Analysis 1. In MaterialTransferManager.cs class Property public ReadOnlyCollection<IMaterialTransfer> MaterialTransfers - Giving exception for materialTransfersLock.ExitReadLock(); Fix - Move the materialTransfersLock.EnterReadLock(); line outside try block. 2. GT from LoadLock to Bufferstation- LOadLock to VacuumChamber works fine. In The VacuumChamber to BufferStation Job - the Material name is coming as Null. Fix: The materialName was not passed at all during Group Transfer. Now, added the matyerial name to the parameters list in the request. 3. In VacuumChamber, register for material tracker location map changed was not happening properly. Corrected it.
30 | CCF Compiler Failure | Fixed |  | Steve | Manu will provide failure details
31 | Supervisor App Config references localhost for the DB and needs to be DataStore | Fixed |  | Steve
32 | Intermediate states such as Shutting Down, Starting Idle are not getting displayed on Title Bar | Fixed |  | Veena | PM ServiceState is getting blocked when a sequence is in progress. We saw that it was blocked for 1:35 minutes during the Idle sequence execution. Analysis still in progress
33 | Turn off the console log sink in the Supervisor | Fixed |  | Mega
33 | Job is not getting executed - Exception is seen | Fixed |  | Mega | After Recipe Execution, transfer operation to move the carrier form PM to Vacuum Chamber is started as per the status in software. But it is not really getting started. Since the operation is in started state, the job is waiting for it to complete. Analysis still in progress The transfer operation to move the carrier out of the PM after recipe execution was started when PM Idle was in progress. Corrected it to start the operation after the PM Idle is complete.
34 | Data is not getting dumped in the CIMStore_Equipment table in DB | Fixed |  | Impana | Till yesterday, we had executed only "Create Veeco DCPs" from VeecoCIMStore.exe. Today, after we executed "Upgrade Veeco DCPs", we could see that the data is getting populated in the DB. Not sure how this is affecting the data population. May be Ashok can explian it.
35 | PM not going to Idle 3 warnings2 alarms-minor deviation alarms related to RMA RC_Oil_SupplyMinorSetpointDeviation, RC_CP_Zone_SupplyMinorSetpointDeviation, RC_CP_Zone_OutletMinorSetpointDeviation | Under Observation |  | Steve | Could not reproduce it till now. Shruti had shared the logs for the run where she observed this behavior. Will analyse the logs after scrum 5/20, 9:45, (Steve) I have seen this issue on my machine, will try to reproduce and look into it. Mega: At Offshore, we saw it about 5 times today in 3 machines
36 | GT is failing b/w bufferstation shelves- Simulator issue | Fixed |  | Shruti | component mismatch was preventing the status of the BufferStation from updating its carrier presence status varaible . Also, when we place carrier from the simulator UI, material map was not being updated. Fixed this
37 | Sometimes some exception related to Cimetrix is seen on supervisor | Under Observation |  | Manu | AddEPT module is throwing exception. Analysis still in progress. Need to discuss with Banu about this.
38 | Once when PM Idle is given , slices went to standby -> modified idle instead of standby->shutdown | Works For Me |  | Ashwin | This issue is not reproducible. Anyone who sees this issue, please share the logs with Ashwin for further analysis
39 | Recipe not executing - Connection to db was lost, after that unable to retrive carrier id dialog pops up continuously. | Fixed |  | Impana | it worked as expected when we created DCPs
40 | Simulator UI - on hovering on components, UI of components will change | Fixed |  | Shankar | Changes made to CCF: \CCF\GUI\GuiCommon\Controls\Buttons\GradientButton.cs Cause : OnmouseEnter event font property of text was reassiging to default value, which is little bigger font will not fit to our simulator controls/components. And this was not happening in the previous version of CCF. Fix : i didn't find any ways to avoid this by trunk changes, so modified the CCF code it self.
41 | Getting Exception from CIM300 - CIM90 during place carrier | Fixed |  | Jayaram/Banu | When place the Carrier in LoadLock getting following exception: Cim300Services Warning Cimetrix.CimControlFramework.FactoryAutomation.Cim300Services.RegisterSubstrate caught System.Collections.Generic.KeyNotFoundException exception. Message: 'The given key was not present in the dictionary.' This was becuase LotId of Wafter was not set. After Set the LotId getting following exception from Cim90.RegisterSubstrate2(material.Name, material.Location, lotId) API. Cim300Services Warning Cimetrix.CimControlFramework.FactoryAutomation.Cim300Services.RegisterSubstrate caught System.Runtime.InteropServices.SEHException exception. Message: 'External component has thrown an exception.' Need to discuss with Banu about this.
42 | Recipe saved dialog box is not being displayed after saving the recipe. But we could see that the DB has an entry for the recipe created | Not an issue |  | Impana | Tested with CCF 3.4 and CCF 3.7 this issue's behavior is expected. Its working fine
43 | Cimetrix.CimControlFramework.FactoryAutomation.COMHelper.TryCOMCall caught System.Runtime.InteropServices.COMException exception from <AddVariable>b__45 103215008:PM1.SDA.InjectorPhantomPanel.Devices.MFC18_SDA_N2_Alkyl_Push_Flow.ValveOverride. Message: 'Error HRESULT E_FAIL has been returned from a call to a COM component.' | Under Observation |  | Steve | 5/20, 9:45, (Steve) So far I can not reproduce this.
44 | InvalidCastException in DataServer | First Chance Exception |  | Steve/Cimetrix | Have sent screen shot of exception on stack trace to Cimetrix.
45 | Unable to delete any newly created Job. | Need to fix | Critical | Veena | Create any new job and try to delete,it fails - vivek Mega: This is a known issue - there is a bug 7454 which amala is working on. Once that bug is fixed, she can merge the change to trunk as well. Workaround is to delete the job again. The job is actually deleted in the supervisor but not reflecting in the OI.
46 | After selecting an job to delete,job is not getting deleted,but the destination station is becoming empty.Logs are in N+2 Folder(cimetrixissues\deletejobissue) | Duplicate of #45 (previous) |  | Mega | Dependant on Item # 45
47 | Unable to create Subloop in some scenario - has copied the logs to N+2 Folder(cimetrixissues\Subloopissue) | Works For Me |  | Lakshmi
48 | Created a recipe - testrrrr - 7 steps - first 3 steps in loop. While executing recipe,click goto and only step 2 and 3 are seen. | Works For Me |  | Manu
49 | Disable Service - IO tab.Not required. | Fixed |  | Mega | This tab is already removed,due to performance issues. Mega: This was enabled in CCF 3.4 before upgrade. It was kept like that in CCF 3.7 also Enable/Disable of this tab is configurable. If user doesn’t want to see this, the flag can be disabled in config file Banu - Verify that the enable/disable feature works. If yes, close this bug
50 | Minimize the OI.It should be Galaxy image and not Cimetrix display. | Need to fix |  | Ashok | As per Ashok, we will take care of it later. It is not critical for now.
51 | Change the Supply panel to Shutdown.PM is in Modified Idle.Click on the "Idle" button.PM doesnot go to Idle and is in still, Idle fault.Logs are in N+2 Folder(cimetrixissues\Supplypaneshutdownlidleissue) | Not an issue |  | Ashwin | Bug id 6926. According to the comments for this bug, this is the expected behavior.
52 | ToBasePressure command not working on VC after abort | Fixed |  | Jayaram
53 | Job is getting aborted due to pick issue in redbull | Fixed | Critical | Shruti | Pick was failing because the location of any shelf in loadlock was always 1. This was due to the new facet map implementation. Corrected this by using the current shelf of the zlift actuator
54 | Job getting aborted due to shutter open time out - Redbull | Works For Me |  | Ashwin
55 | Errors on supervisor when Redbull is configured related to AFI robot and AFI robot remains in "Initialising" state | Fixed |  | Lakshmi
56 | Warnings related to cIMConnect 300 when running Job - Both | In Progress | High | Mega | Have sent screen shot of exception on stack trace to Cimetrix.
57 | Job is getting aborted with Pick fail alarm in lonestar | Works For Me |  | Shruthi | Job executes successfully with no issues
58 | Gt is getting failed to MFI in lonestar | Fixed |  | Veena | The issue is fixed.
59 | Nulll reference in Heater Module - With Hao's commit | Works For Me | High | Shruti | There are no null reference exceptions seen in both lonestar and redbull configuration in the latest trunk
60 | sync issue in MB Cart & Watchdog | In Progress | Critical | Senthil | Sync Failure was due to baratron Pressure failed to reach 0 during Shutdown
61 | VACCUM chmaber is in Initializing | Fixed |  | shruti/Aswin | We saw some exception in the CCF regarding which we have mailed to cimetrix. Until we get a resolution from their end, we cannot proceed Banu - 5/22 I fixed this and committed to the trunk.
62 | Simulator is not updated for MFI | Fixed |  | Veena | The issue is fixed.
63 | Zlift similar to Robot Arm | Fixed |  | Veena | The issue is fixed.
64 | Load and Unload changes | In Progress | High | Shankar
65 | Job is not getting completed - After recipe execution is complete, carrier is not picked from Robot | Fixed |  | Mega
66 | When a carrier is moved from MFI to LL, non acknowledgable alarm is raised saying cannot Load, though carrier is loaded | Need to fix | High | Shankar | Mega: Verify after completing item # 64
67 | Simulator issue- H2 Feed valve for standard slice is shown as false | Fixed |  | Impana | UpdateSupplyValve method is removed, which was causing the issue.
68 | Change the Carrier Id for Group transfer in Operations screen.Go to Automation->Transport module screen.In the Group transfer,Current location is not seen.Only,after changing the carrier Id again,only carrier id is reflected. | Works For Me |  | Veena
69 | Click on the Idle.During Idle sequence,click on the Shutdown button.PM goes to Shutdown state.Lot of sync failure alarms are seen in Alarms screen.Logs are in N+2 Folder(cimetrixissues\Syncafails) | In Progress | Critical | Lakshmi/Sushma Shree | Mega: This is seen even in 3.4. An hidden issue that was found now.
70 | Click on the Idle.During Idle sequence,click on the Shutdown button.PM goes to Shutdown state.In Injector screen and Hydrtides screen,valaves are open.Logs are in N+2 Folder(cimetrixissues\shutdownduringidleissue) | Fixed |  | Sushma Shree
71 | Unload happens , but even then we will an alarm which says "unload failed". | Need to fix | High | Shankar | Mega: Lakshmi, check this behaviour and update after completing item # 64
72 | Job is not getting completed in lonestar configuration. If we execute the Job from MFI, Job is not getting completed. Another inconsistent issue is, Job does not get completed even if we execute the Job from Buffer station or Loadlock. | Need to fix | Critical | Mega
73 | MFI down is allowed when LL door is open and LL has carrier | Need to fix | Critical | Ganga
74 | Start the application, go to automation screen, click on Mode selection and say OK without chaning anything. Result: Vacuum chamber, LLA, LLB, AFI shelves are going to Idle in PM Header. But they are shown as Non initialized in command status table | In Progress | High | Sushma
75 | In PM header it is shown as "Starting Idle" but in Automation screen, inside PM it is shown as "Starting Idle Flow" | Need to fix | High | Amala
76 | If we execute a Job from MFI, Carrier color is not getting changed | Need to fix | High | Amala
77 | Job does not execute if we run 2 jobs | In Progress | Critical | Mega
78 | Job execution is not getting started in redbull- Job remains in setting up state. | Need to fix | Critical | Amala
79 | Group transfer from LLA to LLB failed due to Station is Invalid alarm- Manual place to LLB is also not working after this even after initializing the Robot | Need to fix | Critical | Ashwin
80 | Group transfer from AFI to LLA failed due to an interlock alarm | Need to fix | Critical | Ganga